## general_report
JIRA
Displaying 36 issues at 13/10/2017 06:31 PM.
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Votes | Watchers | Images | Original Estimate | Remaining Estimate | Time Spent | Work Ratio | Sub-Tasks | Linked Issues | Environment | Description | Security Level | Progress | Σ Progress | Σ Time Spent | Σ Remaining Estimate | Σ Original Estimate | Labels | PC Code Approver's Name old | SCCCT-Onshore-BA / PM effort (manday) | Finance & Risk-Onshore-BA / PM effort (manday) | Finance & Risk-Offshore-BA / PM effort (manday) | Finacle-Onshore-BA / PM effort (manday) | Total Cost | Finacle-Offshore-BA / PM effort (manday) | SIT Total Defects | Epic Name for Reporting | SIT Support Mandays | SIT Support Cost | SIT Tester | SIT Testing Status | EBSD | Price Table | SIT Mandays | HLE Received Date | FSD/US Submission Date | HLE Target Date | Initiative | SIT % Execution | Assigned Group | SIT % Success | SIT % Failure | SIT Cost | SIT Actual Mandays | Test Requirements | Delivery Manager | Trainee Name | Google Docs Training Doc | Approx Start Date | Analysis and Design Cost | Build Completion Date | Finacle-Offshore-SIT Support effort (manday) | Analysis and Design Mandays | Finacle-Onshore-SIT Support effort (manday) | Build Mandays | Finacle-Offshore-SIT effort (manday) | Build Cost | Finacle-Onshore-SIT effort (manday) | Category | Finacle-Offshore-Other Support effort (manday) | Finacle-Onshore-Other Support effort (manday) | Data Dictionary Change | Country | Deployment Justification/ Risk | Job Type PMO | CST PMO Delivery Unit | Project Phase | ID | Path | Item Child Count | Item Type | Business Analyst | Non-sensitive Data Verified | Resource | Implementation Ready Date | Severity | Actual Implementation Date | Incident Priority | Impacted Apps | Finacle-Onshore-UAT effort (manday) | LOB Unit | DOA Approved Amount | NCS Onshore Testing | Remaining HLE Cost (SGD $'000) | Cost > UR Approved $ | Original Estimate | Resource Cost | Vendor-Cost | WorkStream | Research Institute | Closed By | Approved By | Markup | Total Resource Cost | Delivery Lead Assigned | GST | ITPS Offshore Testing | ITPS Onshore Testing | User Request (UR) Number | Overall Regression Coverage Comment | Requesting Dept | Overall Regression Coverage | Chargeable | Target Go Live Date Time | UR Sharepoint Link | Funding PC Code | Charging Process | SCV Checklist Testing | FSD/US Internal Review Target Date | FSD/US Internal Review Date | FSD/US Target Signoff Date | Project id | Resolution Type | CST Delivery Unit | Development Description | MJE, IC, CAPEX | Perf Test Comment | Tower Head | Test Description | Vendor Rate | RAG End Date | RAG Start Date | UR App Extension | Standard Rate | Effort Variance (%) | Requested By | Sprint | Budget Owner Entity | Rank | Budget Owner Description | Incident Date | Department | Production Deployment Date | Flagged | Epic/Theme | Regression Start | Request Description | PTS Activity Description | Planned Effort | Requested Start Date | Story Points | Business Value | Regression End | Source Pool Name | Epic Link | Regression Progress | Location | Preventive Actions / Measure | Funding PC Code Location | Staff Entity Code | Source Pool Type | Application Description | Application Code | Original Plan Start | Original Plan End | Cost | Source Pool ID | PTS Activity ID | Function ID | System Live Date | Revised Plan Start | GL Line (Recovery - Cr) | Revised Plan End | GL Line (Charges - Dr) | Code Baseline | Finacle-Offshore-UAT effort (manday) | Level 3 | Level 2 | PROD Environment List | BranchName | Posted in Finance | PO# | Responded Date/Time | Actual Estimate | Closed Date | Function Name | Team | Iteration | Account | Build Version | Clocking Date | Appl_Id | Re-Open? | Task Name | Escalated Date to Vendor | HLE Date | CR Signed Date | Remarks/Memo | Remarks | UR # | Agreement# | Target Completion Date/Time | Include in SLA Computation | Application Name | Billable Amount | Last HLE Date | Rejected By | CR No. | Recurring Bug | Risk Mitigation | CR Submitted Date | Root Cause Classification | Actual Completion Date/Time | CR Pending Approval Date | Section 3: Funding for Definitive Proposal - to proceed the UR for SOW | HLE Approved Date | Root Cause Description | Deployment Plan ID | Progress | SIT Start | Baseline end date | Billable? | Deployment Plan Name | Dev Start | Deployment Plan Version | Dev End | Provider | Change Request Date | Project Name | Tester | Application Name | HLE Provided | Risk Impact | Rejected Date | Risk Likelihood | Finacle Environments List | Affected Components | UAT Signoff | Customer Reporter | SCV Checklist Verified | Baseline start date | Change Request Number(CR) | Expected behaviour | Funding PC Code Name | Preventive Action | Related Problem/SR ID | Start date | Developer | End date | Funding Entity Code | Resolution Date/Time | SIT Signoff Verified | Actual End | Module | UAT Signoff Verified | OpsConnect_id | Reason for rejection | Reason why not meet SLA | Release Notes - Emergency | Change Request Artifact Verified | Defect environment | Analysis of Incident | Affected Items | Finacle SIT Environment | Billing Status | Current behaviour | SIT Signoff Completed | Corrective Action | Function Weights | Reference ID | Defect Details | Epic Status (%) | EBED | ERED | Discounted SLA Days | ERSD | Production Support Type | Steps to Reporoduce | Problem Ticket ID / CR | SCV Checklist Attached | Test Incident Type | Actual Start | Application | MD Approval | Root Cause | Satisfaction Rating | Assigned Date/Time | ESOE | UAT End | Cancel/Reject Date | Delivery Unit Sub-Team | Phase Detected | SIT End | SVC | Developer_OLD | ESTS | % Completion | ESRE | Job Type | Actual Effort Spent (Hours) | Estimated Effort (Hours) | Reported Date/Time | NVA | Defect Category | Detected in Release | Detected in Cycle | SIT No. of Test Cases | Test Level | Detected in System | Detected on Date | Reporting Manager | SRE | Received Date | SOE | Test Type | Defect Status | OIC UAT signoff | Remaining Cost | Defect ID | Reviewer | Build Progress | Funding Country | Resource Type | Actual Mandays | Perf Test Coverage | STS | Staff PC Code | Employee Name | UAT Progress | Estimated Cost | Role | Deployment Risk Mitigation Plan | Team Lead_2 | 1BankID | Approved Date | Target Production Deployment Date | Team Lead_1 | Staff PC Code Description | Parent Link | Team | Regression Test Comment | Security Test Comment | Security Test Coverage | Dev Test Coverage | Customer Change Requestor | Dev Test Comment | EVC | Onshore / Offshore | Regression Test Coverage | UP_Rank | Current Status | Requestor's Manager | AD Release Classification | Requestor | Target Go Live Date | Target Implementation Date | DCIF Application Type | Impacted Systems | UAT Start | Acceptance Testing Required | RAG | Reporting status | Target UAT Date | Employer | Estimate Mandays | HLE Requested Date | Impact Analysis Submitted Date | Approved Mandays | Status | Incident ID | Current Scope_1 | Current Month Cost | Number of Attachments | CST Reference Number | Previous Month Cost | Vendor TL | PC Code Approver's Name ID old | PC Code Approver’s Name ID | Total Mandays | UR Status | PC Code Approver's Name | Release Notes Verified | Support Unit-Onshore-BA / PM effort (manday) | Total Support Mandays | MD Approval Verified | Total Support Cost | UAT Mandays | UR Submission | Last Commenter | Release | UAT Cost | Requirement | UR Issues | UR Prioritization | Design | Vendor SME | SOW | Vendor PM | Resource Allocated | Build
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-297 | Test Greenplum access to parquet in S3 | Story | Backlog | Medium | Unresolved | Unassigned | Hengky KOHAN | Hengky KOHAN | 2017-11-10 19:02 | 2017-12-10 15:22 | 2017-12-10 15:22 | [5 empty] | 0 | 1 | [24 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0h2sd: | [11 empty] | 2 |  |  |  | Data Platform | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Garry STEEDMAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-296 | Test Greenplum alluxio integration | Story | Backlog | Medium | Unresolved | Unassigned | Hengky KOHAN | Hengky KOHAN | 2017-11-10 19:01 | 2017-12-10 15:22 | 2017-12-10 15:22 | [5 empty] | 0 | 1 | [24 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0h2sb: | [11 empty] | 3 |  |  |  | Data Platform | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Garry STEEDMAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-295 | Greenplum Integration with HBase | Story | Backlog | Medium | Unresolved | Unassigned | Hengky KOHAN | Hengky KOHAN | 2017-11-10 15:38 | 2017-12-10 15:22 | 2017-12-10 15:22 | [5 empty] | 0 | 1 | [24 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0h2s7: | [11 empty] | 3 |  |  |  | Data Platform | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Garry STEEDMAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-293 | Automate Alluxio deployment/installation | Story | Done | Medium | Done | Jhalak MODI | Jhalak MODI | Jhalak MODI | 2017-10-10 12:27 | 2017-11-10 15:42 | 2017-12-10 17:50 | 2017-12-10 17:50 |  |  |  |  | 0 | 1 | [24 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0h1an: | [11 empty] | 5 |  |  |  | Data Platform | [31 empty] | None | None | None | [9 empty] | https://w01cdcifjir1a.reg1.1bank.dbs.com:8443/browse/CSTBDANGDP-262 | [112 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Jhalak MODI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-290 | Setup connect direct automation. | Story | Backlog | Medium | Unresolved | Vignesh SHANMUGAKANI | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-09-10 13:55 |  | 2017-10-10 17:17 | [5 empty] | 0 | 2 | [8 empty] | create connect direct script for a component & tdw automation. | [15 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0gzx3: | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-289 | Test 25 copybook and binary file and match result & support | Story | Backlog | Medium | Unresolved | Vignesh SHANMUGAKANI | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-09-10 13:50 |  | 2017-10-10 17:06 | [5 empty] | 0 | 2 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0gzvr: | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-287 | Test 50 copybook and binary file and match result | Story | Backlog | Medium | Unresolved | Ganesh SHANKAR | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-09-10 13:47 |  | 2017-10-10 17:05 | [5 empty] | 0 | 1 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0gzvb: | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-286 | Test 75 copybook and binary file and match result | Story | Backlog | Medium | Unresolved | Harish kumar MALAGA | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-09-10 13:46 |  | 2017-10-10 17:14 | [5 empty] | 0 | 1 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0gzv3: | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-285 | Fix known issues | Story | Backlog | Medium | Unresolved | Unassigned | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-09-10 13:43 |  | 2017-10-10 17:08 | [5 empty] | 0 | 1 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0gzuf: | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [81 empty] | 1. EOF **(**) Siva 2. column name mismatch -> (manually update config file) 3. stackoverflow ** 4. Filtering (row count) => data map => | [40 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-284 | Test 75copybook and binary file | Story | Backlog | Medium | Unresolved | Tushar KUMBHAR | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-09-10 13:42 |  | 2017-10-10 17:14 | [5 empty] | 0 | 1 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0gztr: | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-283 | Test 75 copybook and binary file and match result | Story | Backlog | Medium | Unresolved | Naga DANTANALA | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-09-10 13:41 |  | 2017-10-10 17:14 | [5 empty] | 0 | 1 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0gzsv: | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-278 | SSB Forecast Code Final Tweaks | Story | Dev | High | Unresolved | Sankaranarayanan SHANMUGASUNDARAM | Nakkul SRINIVAS | Nakkul SRINIVAS | 2017-06-10 18:04 | 2017-11-10 15:44 | 2017-11-10 20:03 | [5 empty] | 0 | 2 | [5 empty] | CSTBDANGDP-279, CSTBDANGDP-280, CSTBDANGDP-281 | [18 empty] | CEO Demo | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦hzztox:zw | [11 empty] | 5 |  |  |  | CEO Demo | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Sankaranarayanan SHANMUGASUNDARAM
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-277 | QA - Test files processed on previous sprint. | Story | Backlog | Medium | Unresolved | Unassigned | Ganesh SHANKAR | Ganesh SHANKAR | 2017-06-10 16:30 |  | 2017-10-10 17:06 | [5 empty] | 0 | 1 |  | 1920 | 1920 |  | 0% | [5 empty] | 0% | 0% |  | 1920 | 1920 | [9 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0gxxr: | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0.533 |  | 0.533 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-268 | Install GeoMesa and GeoServer on HBase | Story | Done | Medium | Done | Venkatesh CHIPPA | Jugal MAHANTA | Jugal MAHANTA | 2017-04-10 13:03 | 2017-11-10 19:15 | 2017-11-10 19:18 | 2017-06-10 17:05 |  |  |  |  | 0 | 2 | _thumb_77105.png _thumb_77106.png _thumb_77107.png | 57600 | 0 | 82800 | 143% | [5 empty] | 100% | 100% | 82800 | 0 | 57600 | [9 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 143.75 |  | Sprint 5, Sprint 6 |  | 0¦hzztg8: | [11 empty] | 3 |  |  |  | Data Platform | [31 empty] | None | None | None | [9 empty] | Test the pipe line with sample data,up and running in spark cluster | [112 empty] | 0 |  | 16 | [11 empty] | 23 | [46 empty] | 4 | [15 empty] | Jugal MAHANTA
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-257 | Test ANSP application's copybook and binary files | Story | Backlog | Medium | Unresolved | Tushar KUMBHAR | Tushar KUMBHAR | Tushar KUMBHAR | 2017-03-10 13:40 |  | 2017-06-10 16:49 | [5 empty] | 0 | 1 |  | 144000 | 21600 | 122400 | 85% | [5 empty] | 85% | 85% | 122400 | 21600 | 144000 | [9 empty] | AIX INFA Migration | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 85 |  | Sprint 6 |  | 0¦i0gs4f: | [11 empty] | 2 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 6 |  | 40 | [11 empty] | 34 | [46 empty] | 0 | [15 empty] | Nakkul SRINIVAS
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-247 | Protegrity POC | Story | Backlog | Medium | Unresolved | Tao JIANG | Tao JIANG | Tao JIANG | 28/09/2017 03:51 PM | 2017-12-10 15:23 | 2017-12-10 10:34 | [5 empty] | 0 | 1 | [24 empty] | Technology Evaluation and POC | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦hzztg5:i | [15 empty] | Technology Evaluation and POC | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Tao JIANG
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-241 | Complete 50 copybook and binary file extraction. Fix user mapping To match source system. | Story | To Do | Medium | Unresolved | Dhanalakshmi KOMMAREDDY | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 25/09/2017 06:35 PM |  | 2017-10-10 17:13 | [5 empty] | 0 | 2 | _thumb_75686.png | 32400 | 3600 | 57600 | 177% | [5 empty] | 94% | 94% | 57600 | 3600 | 32400 | [9 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 177.78 |  | Sprint 5, Sprint 6 |  | 0¦hzztg7: | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 1 |  | 9 | [11 empty] | 16 | [46 empty] | 2 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-240 | Test 50 copybook and binary file | Story | To Do | Medium | Unresolved | Tushar KUMBHAR | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 25/09/2017 06:33 PM | 27/09/2017 04:58 PM | 2017-10-10 12:39 | [5 empty] | 0 | 1 | [5 empty] | CSTBDANGDP-245, CSTBDANGDP-263 | [5 empty] | 92% | 43200 | 3600 | 18000 | [9 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 240 |  | Sprint 5, Sprint 6 |  | 0¦hzztg8:xx | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 1 |  | 5 | [11 empty] | 12 | [46 empty] | 0 | [15 empty] | Hengky KOHAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-235 | Create S3 encrypted bucket and automation Job to upload SSB DEMO data from on-prem VM to S3 encrypted bucket | Story | Done | Medium | Done | Tao JIANG | Tao JIANG | Tao JIANG | 25/09/2017 10:21 AM |  | 2017-10-10 12:48 | 25/09/2017 05:08 PM |  |  |  |  | 0 | 1 |  | 57600 | 14400 | 43200 | 75% | [5 empty] | 75% | 75% | 43200 | 14400 | 57600 | [9 empty] | CEO Demo | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 75 |  | Sprint 4, Sprint 5, Sprint 6 |  | 0¦hzztg4: | [11 empty] | 2 |  |  |  | CEO Demo | [31 empty] | None | None | None | [122 empty] | 4 |  | 16 | [11 empty] | 12 | [46 empty] | 0 | [15 empty] | Tao JIANG
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-231 | Join long/lats to ATM data | Story | Dev | Medium | Unresolved | Garry STEEDMAN | Jugal MAHANTA | Jugal MAHANTA | 22/09/2017 07:23 PM | 2017-10-10 13:50 | 2017-10-10 13:50 | [5 empty] | 0 | 4 |  | 25200 | 21600 | 3600 | 14% | [5 empty] | 14% | 14% | 3600 | 21600 | 25200 | [9 empty] | CEO Demo | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 14.29 |  | Sprint 5, Sprint 6 |  | 0¦hzztg8:t | [11 empty] | 1 |  |  |  | CEO Demo | [31 empty] | None | None | None | [122 empty] | 6 |  | 7 | [11 empty] | 1 | [46 empty] | 0 | [15 empty] | Garry STEEDMAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-229 | Design a visualization to render ATM cash withdrawals over time on Geoserver | Story | Dev | Medium | Unresolved | Venkatesh CHIPPA | Jugal MAHANTA | Jugal MAHANTA | 22/09/2017 06:38 PM | 2017-10-10 13:36 | 2017-11-10 19:13 | [5 empty] | 0 | 2 |  | 28800 | 28800 |  | 0% | CSTBDANGDP-294 |  |  |  |  | 0% | 0% |  | 57600 | 57600 | [9 empty] | CEO Demo | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 5, Sprint 6 |  | 0¦hzztg8:p | [11 empty] | 5 |  |  |  | CEO Demo | [31 empty] | None | None | None | [122 empty] | 16 |  | 16 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Jugal MAHANTA
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-228 | Load SG map data in AWS HBase/Geomesa | Story | Dev | High | Unresolved | Sravani BHARUPATI | Jugal MAHANTA | Jugal MAHANTA | 22/09/2017 06:30 PM | 2017-11-10 15:57 | 2017-11-10 20:08 | [5 empty] | 0 | 4 | _thumb_74347.png _thumb_77067.png _thumb_77068.png _thumb_77069.png _thumb_74997.png _thumb_74550.png | 57600 | 21600 | 18000 | 31% | [5 empty] | 45% | 45% | 18000 | 21600 | 57600 | [9 empty] | CEO Demo | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 31.25 |  | Sprint 5, Sprint 6 |  | 0¦hzztg8:h | [11 empty] | 5 |  |  |  | CEO Demo | [31 empty] | None | None | None | [122 empty] | 6 |  | 16 | [11 empty] | 5 | [46 empty] | 6 | [15 empty] | Sravani BHARUPATI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-191 | Run SparkBench against Alluxio/S3 on AWS-CDH-Spark | Story | Done | High | Done | Jugal MAHANTA | Garry STEEDMAN | Garry STEEDMAN | 2017-12-09 14:15 | 2017-11-10 16:15 | 2017-11-10 16:15 | 2017-11-10 11:59 |  |  |  |  | 0 | 2 | [5 empty] | CSTBDANGDP-242 | [5 empty] | 100% | 14400 | 0 | 14400 | [9 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 100 |  | Sprint 5, Sprint 6 |  | 0¦hzztg7:i | [11 empty] | 3 |  |  |  | Data Platform | [31 empty] | None | None | None | [122 empty] | 0 |  | 4 | [11 empty] | 4 | [46 empty] | 0 | [15 empty] | Garry STEEDMAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-173 | Automate AWS S3 Cloudera parcel mirror | Story | Done | Medium | Done | Aditya VARSHNEY | Nakkul SRINIVAS | Nakkul SRINIVAS | 2017-10-09 15:14 | 2017-11-10 14:47 | 2017-12-10 15:31 | 2017-12-10 15:31 |  |  |  |  | 0 | 4 | [5 empty] | CSTBDANGDP-258 | CSTBDANGDP-105 |  |  |  |  | 100% | 64800 | 0 | 57600 | [9 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 112.5 |  | Sprint 4, Sprint 5, Sprint 6 |  | 0¦hzztg0: | [11 empty] | 3 |  |  |  | Data Platform | [31 empty] | None | None | None | [81 empty] | Automate the pulling of updated parcels and repos to the s3 bucket. | [40 empty] | 0 |  | 16 | [11 empty] | 18 | [46 empty] | 1 | [15 empty] | Jhalak MODI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-170 | Automate configuration of TLS encryption levels 0-3 for AWS CDH clusters | Story | Dev | Medium | Unresolved | Jhalak MODI | Garry STEEDMAN | Garry STEEDMAN | 2017-10-09 11:04 | 2017-10-10 13:54 | 2017-10-10 12:39 | [5 empty] | 0 | 1 | [24 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 5, Sprint 6 |  | 0¦hzztg8:xv | [11 empty] | 8 |  |  |  | Data Platform | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Hengky KOHAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-165 | FC FRDM - Get missing files from FRDM | Story | Backlog | Medium | Unresolved | Vamshavardhan KOTHA | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-08-09 11:42 |  | 2017-10-10 17:12 | [5 empty] | 0 | 1 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 5, Sprint 6 |  | 0¦hzztg8:xr | [11 empty] | 5 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-164 | Test 100 copybook and binary file and match result | Story | Backlog | Medium | Unresolved | Vamshavardhan KOTHA | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-08-09 10:58 |  | 2017-10-10 17:14 | [5 empty] | 0 | 1 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0fz8j: | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-163 | extract copybook & binary files & mainframe support. | Story | Backlog | Medium | Unresolved | KARTHIGADEVI J | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-08-09 10:57 |  | 2017-10-10 17:14 | [5 empty] | 0 | 1 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0elog: | [11 empty] | 13 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Lim HONG YI
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-46 | integrate with Data ingestion framework ? | Story | Backlog | Medium | Unresolved | Unassigned | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-04-08 14:01 |  | 25/09/2017 06:27 PM | [5 empty] | 0 | 1 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0elof: | [11 empty] | 13 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Suraj SHRESTHA (TOCST)
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-45 | integrate matching/validation engine | Story | Backlog | Medium | Unresolved | Unassigned | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-04-08 14:01 |  | 2017-10-10 12:39 | [5 empty] | 0 | 1 | [24 empty] | AIX INFA Migration | [10 empty] | UR | [60 empty] | suraj | [21 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 5, Sprint 6 |  | 0¦hzztg8:xi | [11 empty] | 13 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Hengky KOHAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-38 | Test new copybooks & binary files (100) | Story | Backlog | Medium | Unresolved | Tushar KUMBHAR | Suraj SHRESTHA (TOCST) | Suraj SHRESTHA (TOCST) | 2017-04-08 13:56 | 24/09/2017 07:54 PM | 2017-10-10 12:39 | [5 empty] | 0 | 1 | [5 empty] | CSTBDANGDP-107, CSTBDANGDP-108 | CSTBDANGDP-40 | [17 empty] | AIX INFA Migration | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 4, Sprint 5, Sprint 6 |  | 0¦hzztg8:x | [11 empty] | 8 |  |  |  | AIX INFA Migration | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Hengky KOHAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-19 | Demo end-to-end pipeline on AWS and on-prem | Story | Backlog | Medium | Unresolved | Garry STEEDMAN | Hengky KOHAN | Hengky KOHAN | 31/07/2017 04:09 PM | 2017-11-10 15:44 | 2017-11-10 15:44 | [5 empty] | 0 | 1 | [24 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0elnn: | [11 empty] | 8 |  |  |  | Data Platform | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Garry STEEDMAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-14 | Build CI/CD pipeline for all cloud/on-prem envs | Story | Dev | Medium | Unresolved | Lavanya THOTA | Hengky KOHAN | Hengky KOHAN | 31/07/2017 04:04 PM | 2017-12-10 12:46 | 2017-12-10 13:16 | [5 empty] | 0 | 5 | _thumb_76876.png _thumb_77051.png _thumb_77101.png _thumb_77325.png _thumb_77326.png | 59400 | 10800 | 77400 | 130% | [5 empty] | 87% | 87% | 77400 | 10800 | 59400 | [9 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 130.3 |  | Sprint 5, Sprint 6 |  | 0¦hzztg8:w | [11 empty] | 8 |  |  |  | Data Platform | [31 empty] | None | None | None | [122 empty] | 3 |  | 16.5 | [11 empty] | 21.5 | [46 empty] | 10 | [15 empty] | Lavanya THOTA
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-12 | Test data replication mechanism from CDH on-prem to CDH AWS and back | Story | Backlog | Medium | Unresolved | Garry STEEDMAN | Hengky KOHAN | Hengky KOHAN | 31/07/2017 04:04 PM |  | 24/09/2017 07:22 PM | [5 empty] | 0 | 1 | [8 empty] | * Test replication from AWS Accumulo to on-prem Accumulo and back * Test HDFS replication from AWS to on-prem and back | [15 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 6 |  | 0¦i0elmf: | [11 empty] | 5 |  |  |  | Data Platform | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Garry STEEDMAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-11 | Setup and deploy Data Ingestion framework to on-prem dev env | Story | To Do | Medium | Unresolved | Suraj SHRESTHA (TOCST) | Hengky KOHAN | Hengky KOHAN | 31/07/2017 04:01 PM | 2017-10-10 10:45 | 2017-10-10 12:39 | [5 empty] | 0 | 1 | [24 empty] | FC-FRDM Ingestion | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 0 |  | Sprint 5, Sprint 6 |  | 0¦hzztg8:v | [11 empty] | 1 |  |  |  | FC-FRDM Ingestion | [31 empty] | None | None | None | [122 empty] | 0 |  | 0 | [11 empty] | 0 | [46 empty] | 0 | [15 empty] | Hengky KOHAN
CST-BDA_NextGen_Data_Platform | CSTBDANGDP-6 | Set up Greenplum environment | Story | Backlog | Medium | Unresolved | Tao JIANG | Hengky KOHAN | Hengky KOHAN | 31/07/2017 03:57 PM |  | 2017-12-10 10:34 | [5 empty] | 0 | 2 |  | 86400 | 57600 | 28800 | 33% |  |  |  | Setup object store and HBase as under storage for Greenplum. Test the Greenplum SQL query performance over parquet file in object store or HBase tables. |  | 33% | 33% | 28800 | 57600 | 86400 | [9 empty] | Data Platform | [10 empty] | UR | [82 empty] | Baseline End Date isn't filled | Baseline Start Date isn't filled |  |  | 33.33 |  | Sprint 2, Sprint 6 |  | 0¦hzztg5: | [11 empty] | 13 |  |  |  | Data Platform | [31 empty] | None | None | None | [122 empty] | 16 |  | 24 | [11 empty] | 8 | [46 empty] | 0 | [15 empty] | Tao JIANG
Generated at Fri Oct 13 18:31:33 SGT 2017 by Garry STEEDMAN using JIRA 7.0.4#70113-sha1:3aced62b70c5551ecfbe55e1ed91a8d97bc84e9d.